## Financials
SmartShop E-Commerce Project Financials
Project Duration: 12 Weeks (Jan 16 – Apr 9, 2026)
Maximum Project Budget: $21,000
Week 8
Prepared by Team: Smart Tech | Date: 02/24/2026
1. PROJECT BUDGET (PLANNED)
A. Labor Costs
Role and Name | Hourly Rate | Planned Hours | Total Cost
Project Manager Abdul Choudhary | $30/hr | 150 | $4,500
Frontend Developer Vrushika Gajjar | $25/hr | 200 | $5,000
Backend Developer Aqveena Manoj | $30/hr | 200 | $6,000
Database Administrator Devam Trivedi | $25/hr | 80 | $2,000
Security Specialist Abdul Munshi | $30/hr | 80 | $2,400
Total Labor Cost |  |  | $19,900
B. Technology Costs (VPS-Based)
Item | Cost
VPS Hosting (3 months × $12) | $36
Domain Name | $15
SSL Certificate | $20
Email Service (3 months) | $30
Payment Gateway Setup | $100
Design Assets | $150
Total Technology Cost | $351
C. Training
Item | Cost
User/Admin Training Materials | $200
Total Training Cost | $200
D. Miscellaneous
Item | Cost
Office Supplies / Internet | $249
Travel / Meetings | $300
Total Miscellaneous | $549
TOTAL PROJECT BUDGET
Category | Cost
Labor | $19,900
Technology | $351
Training | $200
Miscellaneous | $549
Grand Total | $21,000
2. BUDGET VS ACTUAL
Category | Planned | Actual | Variance
Labor | $19,900 | $19,600 | -$300
Technology | $351 | $380 | +$29
Training | $200 | $180 | -$20
Miscellaneous | $549 | $500 | -$49
Total Actual Cost | $21,000 | $20,660 | Under budget by $340
3. POST-IMPLEMENTATION OPERATIONAL COSTS (ANNUAL)
A. Ongoing Labor (6 hours/week)
Role | Hours/Week | Rate | Annual Cost
System Support/Admin | 6 hrs | $25/hr | $7,800
Total Ongoing Labor |  |  | $7,800
B. Ongoing Technology
Item | Annual Cost
VPS Hosting (12 × $12) | $144
Domain Renewal | $15
SSL Renewal | $20
Email Service | $120
Maintenance Tools | $200
Total Technology Cost | $499
TOTAL ANNUAL OPERATIONAL COST | $8,299
4. REVENUE PROJECTION
Orders per Day | 15
Average Order Value | $35
Monthly Revenue | 15 × 35 × 30 = $15,750
Annual Revenue | $15,750 × 12 = $189,000
Assume 30% cost of goods sold
Net Revenue After Product Cost | $189,000 × 70% = $132,300
5. NET PROFIT AFTER OPERATIONAL COST
Annual Net Revenue | $132,300
Annual Operational Cost | $8,299
Estimated Annual Profit | $124,001
6. EXPECTED VALUE IMPACT
• Enable 24/7 online sales
• Reduce manual order handling
• Automate inventory and stock tracking
• Expand customer reach
• Increase revenue without extra physical store costs
• Provide scalable, low-maintenance growth
7. ROI (RETURN ON INVESTMENT)
Initial Investment | $21,000
Annual Profit | $124,001
ROI Payback Period | ~2–3 months after launch